D8 WORKING GROUP ON MARINE AND FISHERIES

TECHNICAL COPERATION AND CAPACITY BUILDING FOR AQUACULTURE

A PROPOSAL

BY THE GOVERNMENT OF MALAYSIA

TECHNICAL COOPERATION FOR DEVELOPMENT AND MANAGEMENT OF GENETICALLY IMPROVED TILAPIA BROODSTOCK

Department of Fisheries

Ministry of Agriculture and Agro-Based Industry

Aras 1-6, Blok Menara 4G2, Precinct 4, 62628 Putrajaya Malaysia

1  	PRINCIPAL

| A. | Title | : | Technical Cooperation for Development and Management of Genetically Improved and Disease Free Tilapia Stock |
| --- | --- | --- | --- |
| B. | Lead Agency | : | Department of Fisheries Malaysia |
|  | Co-leads | : | Mohd. Fariduddin B.Othman, PhD Azhar B. Ahmad, PhD |
| C. | Other Organisation Involved | : | WorldFish Centre (WFC), Malaysia |

D. Brief description of the project and its proposed objectives, outputs/outcomes:

Following the 4th D8 meeting of the WGMAF in Nigeria in 2013, this project was formulated based on the current needs of D8 countries regarding tilapia (GIFT) breeding program. It focuses on technology transfer, knowledge and resource sharing among D8 countries.

2	PROPOSED OBJECTIVES

  - In collaboration with WFC, Malaysia will  provide technical expertise and assistance to relevant D8 member countries on development of genetically improved tilapia breeding program.

  - In collaboration with the WFC, Malaysia will provide technical expertise and assistance to relevant D8 member countries on tilapia GIFT  breeding and proper dissemination of seed.

  - To introduce and to share Malaysia’s newly developed Streptococcus vaccine for tilapia to any interested D8 countries.

  - To promote knowledge and experience sharing among D8 member countries on the production of disease free tilapia stock in light of the establishment of Nucleus Breeding Centre or Brood stock Multiplication Centre), farming, certification systems and enhancement of tilapia quality.

- OUTPUT / OUTCOME

  - Systematic D8 collaboration among the tilapia industries community.

- Substantial economic benefit to farmers and member countries

- Helping in the commercialization of the tilapia Streptococcus vaccine.

- Increase in efficiency and sustainability in tilapia production activities

- PURPOSE AND SIGNIFICANCE

  - Tilapia is one of the important aquaculture species in Malaysia and also to other D8 member countries. Of late in Malaysia, tilapia has been designated as high priority commodity and  has further incorporated as an Entry Point Project,  under National Key Economic Areas (NKEA) initiative since the last 3 years.

  - Despite the potential, one of the biggest obstacles in tilapia production in the country is inadequate seed supply. This is mainly due to insufficient availability of high quality strain, lack or poor brood stock management, lack of bio-safety measures and regulations and disease related problems.

  - Beside the red tilapia hybrid, Genetically Improved Farmed Tilapia (GIFT) is one of the establish tilapia strains developed by WorldFish Centre (WFC) in Malaysia. GIFT from Malaysia has been disseminated to 11 countries in the Asia Pacific regions and to Brazil and Costa Rica in Latin America. The GIFT tilapia experience highlighted the need for an institutionalization of a country specific follow up program once the strain has been transferred and disseminated.

  - The effective dissemination of the improved strain poses a major challenge, and skilled human resources have to be assigned the task of ensuring the fish reach the farmers. Malaysia is fortunate because it has been involved in the tilapia (Red and GIFT) breeding program through collaboration with WFC since the year 2001. Malaysia has acquired substantial skills and technical know-how in this aspect.

  - In addition, Malaysia, through the National Fish Health Research Centre (NaFish) has recently launched its first Streptococcus vaccine for tilapia.

  - In view of this, Malaysia would like to share related experience and expertise among D8 member countries. Malaysia would like to take this forum to propose a cooperation program on tilapia management and development of disease free stock among D8 member countries.

5	ACTIVITIES, PLAN OF WORK, AND TIME TABLE

| No. | Activities | Plan of activities | Proposed date |
| --- | --- | --- | --- |
| Objective 1 | - Conduct training courses (1 month) on tilapia broodstock management and seed dissemination. - Working attachment (1 -6 months) at relevant research institution (Fisheries Research Institute, WorldFish Centre). | 1 participant/ country 2 participants/ year | 2015 2016 |
| Objective 2 | - Validation of newly developed tilapia Streptococcus vaccine in 1 interested D8 countries | Validation activity in one country | 2015-2016 |
| Objective 3 | - Field visit to tilapia farm/hatchery in D8 member countries. - Assist/Acquire knowledge and skill in developing and strengthening biosecurity measures and certification for hatchery/farm. - Attain expertise in enhancing tilapia quality (eg. to remove off flavour) | 2 participant/ country Annual meeting Workshop (beginning, mid-term and end of project) | 2016 2015, 2016 2015-2016 |

6	COMMUNICATING THE RESULTS  – Academic Community

  - Manual on tilapia breeding and fry production.

  - Annual meeting

  - Publication of Newsletter and progress report

- COMMUNICATING THE RESULTS – Practitioner Community

  - Manual on tilapia breeding and fry production.

  - Manual/Standard Operating Procedures (eg. MyGAP)

8	BUDGET AND CONTRIBUTIONS

| Category | Requested of | Other possible contributors |
| --- | --- | --- |
| Objective 1 | *D8 secretariat/executive committee | OIC, ADB, D8 Member countries |
| Objective 2 |  |  |
| Objective 3 |  |  |

Note: *The detailed financial requirement will be supplied if this proposal is accepted by the D8 secretariat/executive committee.