PROGRESS WORK PROGRAMMES OF D-8 WORKING GROUP ON MARINE AFFAIRS AND FISHERIES

(Dec 2013 - Nov 2014)

| NO | SCOPE OF WORKS | Projects/Activities | TIMELINE | DELIVERABLES | INDICATORS | BUDGET | REMARKS | PROGRESS (Dec 2013-Nov 2014) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | INTRA-TRADE | Facilitation |  | Awareness creation, coordination and information sharing, and interaction | Number of businesses established | As agreed by member States | Nigeria will develop for the Intra Trade | NOT YET |
|  |  | Private Sector Interaction/Business Forum | Mid February | Business developed | Number of businesses established | As agreed by member States | Nigeria to develop proposal by mid February | NOT YET |
|  |  | Media Promotion |  | More Awareness created | Information disemination and website established | member States | Nigeria would manage and coordination the website | NOT YET |
|  |  | Linkages Interaction between stakeholders |  | Information sharing | Improved partnership and collaboration |  | all member states | NOT YET |
| 2 | MUTUAL ARRANGEMENT | Continuous interactions and collaborations | all year around | sharing of experiences of member states | mutual understanding established | As agreed by member states |  | NOT YET |
| 3 | MONITORING | Tracking and assessments of performance | all year around | Periodic Reports of achievements | Status of completion of projects and programmes | As agreed by member states | Nigeria to develop the proposal | NOT YET |
| 4 | PRODUCT/TECHNOLOGY DEVELOPMENT, RESEARCH & EXHIBITION | Exhibition & Business Forum | May 2014 | Exhibitions, Side Talks, Interactive Sessions, Flyers, Brochures | Number of product exhibited and markets established | Indonesia will provide the necessary logistic | Indonesia has held " Indonesia Marine and Fisheries Expo and Conference (IMFEC)" on 27-29 August 2014 in Jakarta in order to promote product/technology development, research and exhibition activity/ works within D-8 Member countries. | Indonesia Marine and Fisheries Expo and Conference (IMFEC) held on 27-29 August 2014 in Jakarta host by Directorate General of Fisheries Product Processing and Marketing-Ministry of Marine Affairs and Fisheries of Republic of Indonesia (MMAF) and attended CEOs, Entrepreneurs, SMEs, researchers, government, international organization,NGO, stakeholders in marine, fisheries, and tourism industry and also attended participants from officials/representatives/embassy of each D-8 Countries to Indonesia. Also during the IMFEC, officials from MMAF and General Directorate of Fisheries and Aquaculture (GDFA) of the Republic of Turkey had an informal discussion meeting to share ideas, information, and cooperation in order to the development of the D-8 Working Group on Marine Affairs and Fisheries (WGMAF), as well as listened presentation which title “Turkey Fisheries and Aquaculture Status and Prospects" and “draft project on Training of Trainers for Aquaculture extention and Technique for D-8 Member Countries." |
|  |  | Research Development |  | improve the new strategies and innovation | Skills and capacity development | As agreed by member states | Turkey to develop the proposal by the mid February 2014 | On 28 August 2014, Official from General Directorate of Fisheries and Aquaculture (GDFA) of the Republic of Turkey delivered presentation which title “draft project on Training of Trainers for Aquaculture extention and Technique for D-8 Member Countries " to officials from MMAF-Indonesia during Indonesia Marine Expo and Conference in Jakarta. Further discussion on this draft project will be discuss in the 5th WGMAF meeeting in Istanbul, Turkey on 1 December 2014. |
| 5 | COMMON VISION FOR SUSTAINABILITY OF MARINE AFFAIRS | Standardisation, certification, stock assessment and enforcement |  | level compliance with national and global laws and regulations | enhanced confirmity and harmonization with global standards and rules | As agreed by member states | Pakistan to develop proposal by mid February 2014 | NOT YET |
| 6 | INFORMATION SHARING/LINKAGES MEDIA PROMOTIONS | Media, publication, information disemination, electronic means of interactions |  | Sharing of success story of implemention of policies and programmes | Additional means of collaboration, partnership and interactions | As agreed by member states | Malaysia to develop the proposal by mid February 2014 | on May 26th, 2014. Malaysia submitted a proposal for media publication,information dissemination, electronic means of interactions for countries of D-8 Scope of Proposal: (1). List of Existing Application System at Department of Fisheries (2). List of Publications – website for Department of Fisheries *Malaysia Delegation delivered those proposals in the Forum D-8 WGMAF in Izmir, Turkey on 6 June 2014 |
| 7 | COMMERCIAL DEVELOPMENT OF TILAPIA SPECIES, MARICULTURE & CAGECULTURE | Exhibition & Business Forum , training, study tours and capacity development |  | Improve product and processing equipment | More production and sales | As agreed by member states | Egypt to advised to attend the next meeting and develop proposal by mid February 2014 | NOT YET |